## README
Resource & Planning Dashboard Workbook (Template v2)
Fill the input tabs (Projects, Engineers, Planned_ProjectMonth, Planned_Allocations, Actual_Hours, Skills, Lab_Tech_Hours, Milestones). Dashboard visuals update from those tables.
Selectors: Use Params to choose SelectedMonth and SelectedProject. Optional: add Excel Form Control sliders and link them to Params cells.

## Months
Month | MonthIndex | MonthLabel
2026-01-01 | 1 | 2026-01
2026-02-01 | 2 | 2026-02
2026-03-01 | 3 | 2026-03
2026-04-01 | 4 | 2026-04
2026-05-01 | 5 | 2026-05
2026-06-01 | 6 | 2026-06
2026-07-01 | 7 | 2026-07
2026-08-01 | 8 | 2026-08
2026-09-01 | 9 | 2026-09
2026-10-01 | 10 | 2026-10
2026-11-01 | 11 | 2026-11
2026-12-01 | 12 | 2026-12

## Projects
ProjectID | ProjectName | Type | WorkClass
R1337.1 | K4.0 Resi Concealed Sidewall | NPD | Planned
R1337.3 | K5.6 Resi Concealed Sidewall | NPD | Planned
R1337.2 | K8.0 Resi Concealed Sidewall ECLH | NPD | Planned
R1430.1A | K11.2 Low Profile In Rack Storage Sprinkler | NPD | Planned
R1430.1B | K8.0 Low Profile In Rack Storage Sprinkler | NPD | Planned
R1430.1C | K5.6 Low Profile In Rack Storage Sprinkler | NPD | Planned
R1514.1 | K4.9 Resi Concealed Pendent | NPD | Planned
R1514.2 | K3.0 Resi Concealed Pendent | NPD | Planned
R1517 | K22/K25 ESFR High Pressure | NPD | Planned
R1517.1 | K17 ESFR High Pressure | NPD | Planned
R1518 | Universal Cleanroom | NPD | Planned
R1527 | UL Listing for Vortex | NPD | Planned
S0001 | V10 Spray Nozzle Kfactor Noncompliance | Sustaining | Unplanned/Firefighting
S0057 | VicFlex Double Window VB5 Data Center Bracket | Sustaining | Planned
S0013 | VicFlex AH1/AH2 Dual Sourced Crimp Nut | Sustaining | Planned
S0062 | VTI 300 Bar Cylinder Valve | Sustaining | Planned
R0999 | Out of Office (PTO/Holiday) | Out of Office | Planned
R0996 | Administrative Work | Admin | Planned
S0004 | Regulatory Support / Industry Committee Work | Sustaining | Planned
R0992 | Applications / Sales Support | Sustaining | Unplanned/Firefighting
S0002 | EP Support | Sustaining | Unplanned/Firefighting
S0005 | Manufacturing Support | Sustaining | Unplanned/Firefighting
R0991 | Lab 5S Support | Sustaining | Unplanned/Firefighting
S0006 | Submittal Modifications | Sustaining | Planned
S0082 | Vortex Sustaining | Sustaining | Planned
S0013 | General Sustaining Support | Sustaining | Planned
R0751 | QA / PER Support | Sustaining | Unplanned/Firefighting
S0008 | Drawing Maintenance | Sustaining | Unplanned/Firefighting
S0003 | Reliability Growth (Green Belt, etc.) | Sustaining | Unplanned/Firefighting
R0993 | Product Engineering Support | Sustaining | Unplanned/Firefighting
S0001 | Product Disruption | Sustaining | Unplanned/Firefighting
R0997 | Training | Sustaining | Planned
T1528 | V2603 Foam Nozzle | Sprint | Planned

## Engineers
Engineer | CapacityOverrideHours
Mike | 0
Karl | 0
Brian | 0
Hannah | 0
Marcelo | 0
Justin | 0
Aaron | 0

## Skills
Engineer | FEA | CFD | Deflector development | VicFlex hose | VicFlex bracket | Vortex design | Vortex operation | Data acquisition | Fire test protocols | Failure / root cause analysis | Statistical analysis | Test fixture design | Codes and standards | Tolerance stackup
Mike | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Karl | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hannah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marcelo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Justin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aaron | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Milestones
ProjectID | DR1 | DR2 | DR3 | Launch
R1337.1
R1337.3
R1337.2
R1430.1A
R1430.1B
R1430.1C
R1514.1
R1514.2
R1517
R1517.1
R1518 | 2025-02-04 | 2025-06-12 | 2026-03-13 | 2026-10-01
R1527

## Planned_ProjectMonth
Month | ProjectID | TotalPlannedHours
2026-01-01 | R1337.1 | 40
2026-01-01 | R1337.3 | 40
2026-01-01 | R1337.2 | 40
2026-01-01 | R1430.1A | 120
2026-01-01 | R1430.1B | 60
2026-01-01 | R1430.1C | 60
2026-01-01 | R1514.1 | 30
2026-01-01 | R1514.2 | 60
2026-01-01 | R1517
2026-01-01 | R1517.1 | 120
2026-01-01 | R1518 | 60
2026-01-01 | R1527 | 120
2026-01-01 | S0001 | 10
2026-01-01 | S0057 | 30
2026-01-01 | S0013 | 15
2026-01-01 | S0062 | 60

## Planned_Allocations
Month | ProjectID | Engineer | AllocationPct | ProjectType | PlannedHoursAllocated
2026-01-01 | R1337.1 | Marcelo | 100% | NPD | 10
2026-01-01 | R1337.3 | Marcelo | 100% | NPD | 10
2026-01-01 | R1337.2 | Marcelo | 100% | NPD | 10
2026-01-01 | R1430.1A | Mike | 100% | NPD | 120
2026-01-01 | R1430.1B | Marcelo | 100% | NPD | 120
2026-01-01 | R1430.1C | Justin | 100% | NPD | 120
2026-01-01 | R1514.1 | Mike | 100% | NPD | 10
2026-01-01 | R1514.2 | Justin | 100% | NPD | 10
2026-01-01 | R1517 |  |  | NPD
2026-01-01 | R1517.1 | Hannah | 100% | NPD | 120
2026-01-01 | R1518 | Brian | 100% | NPD | 60
2026-01-01 | R1527 | Aaron | 100% | NPD | 60
2026-01-01 | S0057 | Brian | 100% | Sustaining | 10
2026-01-01 | S0062 | Aaron | 100% | Sustaining | 60
2026-01-01 | T1528 | Karl | 100% | Sprint | 10

## Actual_Hours
Month | ProjectID | Engineer | WorkClass | ProjectType | ActualHours
2026-01-01 | R1430.1A | Mike | Planned | NPD | 166
2026-01-01 | R0999 | Mike | Planned | Out of Office | 8
2026-01-01 | R0996 | Mike | Planned | Admin | 2
2026-01-01 | R1518 | Brian | Planned | NPD | 42.75
2026-01-01 | S0004 | Brian | Planned | Sustaining | 27
2026-01-01 | R0992 | Brian | Unplanned/Firefighting | Sustaining | 19.75
2026-01-01 | R0996 | Brian | Planned | Admin | 18.5
2026-01-01 | R0999 | Brian | Planned | Out of Office | 16
2026-01-01 | S0062 | Brian | Planned | Sustaining | 13.75
2026-01-01 | S0002 | Brian | Unplanned/Firefighting | Sustaining | 8
2026-01-01 | S0005 | Brian | Unplanned/Firefighting | Sustaining | 6.5
2026-01-01 | R0991 | Brian | Unplanned/Firefighting | Sustaining | 6.5
2026-01-01 | S0006 | Brian | Planned | Sustaining | 4.5
2026-01-01 | S0082 | Brian | Planned | Sustaining | 4
2026-01-01 | R1337.2 | Brian | Planned | NPD | 3
2026-01-01 | S0057 | Brian | Planned | Sustaining | 2
2026-01-01 | S0013 | Brian | Planned | Sustaining | 2
2026-01-01 | R0751 | Brian | Unplanned/Firefighting | Sustaining | 1.5
2026-01-01 | S0008 | Brian | Unplanned/Firefighting | Sustaining | 0.25
2026-01-01 | R1517.1 | Hannah | Planned | NPD | 143.5
2026-01-01 | R0996 | Hannah | Planned | Admin | 21.5
2026-01-01 | S0003 | Hannah | Unplanned/Firefighting | Sustaining | 3
2026-01-01 | R1430.1B | Marcelo | Planned | NPD | 71.5
2026-01-01 | R1430.1A | Marcelo | Planned | NPD | 45.75
2026-01-01 | R0999 | Marcelo | Planned | Out of Office | 28
2026-01-01 | R1337.1 | Marcelo | Planned | NPD | 22.5
2026-01-01 | R0996 | Marcelo | Planned | Admin | 14
2026-01-01 | R1337.3 | Marcelo | Planned | NPD | 22.5
2026-01-01 | R0993 | Marcelo | Unplanned/Firefighting | Sustaining | 1
2026-01-01 | R1514.2 | Justin | Planned | NPD | 58.5
2026-01-01 | R1430.1C | Justin | Planned | NPD | 39.5
2026-01-01 | R1430.1A | Justin | Planned | NPD | 23.5
2026-01-01 | S0001 | Justin | Unplanned/Firefighting | Sustaining | 20
2026-01-01 | R0996 | Justin | Planned | Admin | 17.5
2026-01-01 | R0999 | Justin | Planned | Out of Office | 8
2026-01-01 | R0997 | Justin | Planned | Sustaining | 3
2026-01-01 | S0004 | Justin | Planned | Sustaining | 3
2026-01-01 | S0003 | Justin | Unplanned/Firefighting | Sustaining | 2
2026-01-01 | R1514.2 | Justin | Planned | NPD | 1
2026-01-01 | S0062 | Aaron | Planned | Sustaining | 57
2026-01-01 | R0999 | Aaron | Planned | Out of Office | 36
2026-01-01 | R1527 | Aaron | Planned | NPD | 30
2026-01-01 | R0992 | Aaron | Unplanned/Firefighting | Sustaining | 17
2026-01-01 | R0991 | Aaron | Unplanned/Firefighting | Sustaining | 16
2026-01-01 | S0082 | Aaron | Planned | Sustaining | 13.5
2026-01-01 | R0996 | Aaron | Planned | Admin | 6.5

## Lab_Tech_Hours
Month | Engineer | LabTechHours
2026-01-01 | Mike | 1
2026-01-01 | Karl | 0
2026-01-01 | Brian | 26.25
2026-01-01 | Hannah | 28.5
2026-01-01 | Marcelo | 70.25
2026-01-01 | Justin | 70
2026-01-01 | Aaron | 0
2026-02-01 | Mike | 8
2026-02-01 | Karl | 0
2026-02-01 | Brian | 11.25
2026-02-01 | Hannah | 6
2026-02-01 | Marcelo | 11
2026-02-01 | Justin | 16
2026-02-01 | Aaron | 5

## Params
Parameter | Value
StdMonthlyCapacityHours | 140
SelectedMonth | 2026-01-01
SelectedProject | R1518
OverUtilizationThresholdPct | 1

## Calc
Calculated summaries (do not edit)
SelectedMonth | 2026-01-01 |  | SelectedProject | R1518
MonthLabel | Planned_NPD | Planned_Sustaining | Planned_Sprint | Actual_NPD | Actual_Sustaining | Actual_Sprint | Actual_Firefighting | LabTech_Total | MonthDate
2026-01 | 650 | 70 | 10 | 670 | 231.25 | 0 | 101.5 | 196 | 2026-01-01
2026-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.25 | 2026-02-01
2026-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-03-01
2026-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-04-01
2026-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-05-01
2026-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-06-01
2026-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-07-01
2026-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-08-01
2026-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-09-01
2026-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-10-01
2026-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-11-01
2026-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026-12-01
MonthLabel | Planned_SelectedProject | Actual_SelectedProject | MonthDate
2026-01 | 60 | 42.75 | 2026-01-01
2026-02 | 0 | 0 | 2026-02-01
2026-03 | 0 | 0 | 2026-03-01
2026-04 | 0 | 0 | 2026-04-01
2026-05 | 0 | 0 | 2026-05-01
2026-06 | 0 | 0 | 2026-06-01
2026-07 | 0 | 0 | 2026-07-01
2026-08 | 0 | 0 | 2026-08-01
2026-09 | 0 | 0 | 2026-09-01
2026-10 | 0 | 0 | 2026-10-01
2026-11 | 0 | 0 | 2026-11-01
2026-12 | 0 | 0 | 2026-12-01
ProjectIndex | EngineerIndex | PlannedHours
1 | 1 | 0
1 | 2 | 0
1 | 3 | 0
1 | 4 | 0
1 | 5 | 10
1 | 6 | 0
1 | 7 | 0
2 | 1 | 0
2 | 2 | 0
2 | 3 | 0
2 | 4 | 0
2 | 5 | 10
2 | 6 | 0
2 | 7 | 0
3 | 1 | 0
3 | 2 | 0
3 | 3 | 0
3 | 4 | 0
3 | 5 | 10
3 | 6 | 0
3 | 7 | 0
4 | 1 | 120
4 | 2 | 0
4 | 3 | 0
4 | 4 | 0
4 | 5 | 0
4 | 6 | 0
4 | 7 | 0
5 | 1 | 0
5 | 2 | 0
5 | 3 | 0
5 | 4 | 0
5 | 5 | 120
5 | 6 | 0
5 | 7 | 0
6 | 1 | 0
6 | 2 | 0
6 | 3 | 0
6 | 4 | 0
6 | 5 | 0
6 | 6 | 120
6 | 7 | 0
7 | 1 | 10
7 | 2 | 0
7 | 3 | 0
7 | 4 | 0
7 | 5 | 0
7 | 6 | 0
7 | 7 | 0
8 | 1 | 0
8 | 2 | 0
8 | 3 | 0
8 | 4 | 0
8 | 5 | 0
8 | 6 | 10
8 | 7 | 0
9 | 1 | 0
9 | 2 | 0
9 | 3 | 0
9 | 4 | 0
9 | 5 | 0
9 | 6 | 0
9 | 7 | 0
10 | 1 | 0
10 | 2 | 0
10 | 3 | 0
10 | 4 | 120
10 | 5 | 0
10 | 6 | 0
10 | 7 | 0
11 | 1 | 0
11 | 2 | 0
11 | 3 | 60
11 | 4 | 0
11 | 5 | 0
11 | 6 | 0
11 | 7 | 0
12 | 1 | 0
12 | 2 | 0
12 | 3 | 0
12 | 4 | 0
12 | 5 | 0
12 | 6 | 0
12 | 7 | 60
13 | 1 | 0
13 | 2 | 0
13 | 3 | 0
13 | 4 | 0
13 | 5 | 0
13 | 6 | 0
13 | 7 | 0
14 | 1 | 0
14 | 2 | 0
14 | 3 | 10
14 | 4 | 0
14 | 5 | 0
14 | 6 | 0
14 | 7 | 0
15 | 1 | 0
15 | 2 | 0
15 | 3 | 0
15 | 4 | 0
15 | 5 | 0
15 | 6 | 0
15 | 7 | 0
16 | 1 | 0
16 | 2 | 0
16 | 3 | 0
16 | 4 | 0
16 | 5 | 0
16 | 6 | 0
16 | 7 | 60
ProjectIndex | DR1 | DR2 | DR3 | Launch
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0
6 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0
11 | 45692 | 45820 | 46094 | 46296
12 | 0 | 0 | 0 | 0
Planned vs Actual (Stacked) helper
Category | NPD | Sustaining | Sprint
2026-01 Planned | 650 | 70 | 10
2026-01 Actual | 670 | 231.25 | 0
2026-02 Planned | 0 | 0 | 0
2026-02 Actual | 0 | 0 | 0
2026-03 Planned | 0 | 0 | 0
2026-03 Actual | 0 | 0 | 0
2026-04 Planned | 0 | 0 | 0
2026-04 Actual | 0 | 0 | 0
2026-05 Planned | 0 | 0 | 0
2026-05 Actual | 0 | 0 | 0
2026-06 Planned | 0 | 0 | 0
2026-06 Actual | 0 | 0 | 0
2026-07 Planned | 0 | 0 | 0
2026-07 Actual | 0 | 0 | 0
2026-08 Planned | 0 | 0 | 0
2026-08 Actual | 0 | 0 | 0
2026-09 Planned | 0 | 0 | 0
2026-09 Actual | 0 | 0 | 0
2026-10 Planned | 0 | 0 | 0
2026-10 Actual | 0 | 0 | 0
2026-11 Planned | 0 | 0 | 0
2026-11 Actual | 0 | 0 | 0
2026-12 Planned | 0 | 0 | 0
2026-12 Actual | 0 | 0 | 0
NPD Projects Planned vs Actual (SelectedMonth)
NPD_Project | PlannedHours | ActualHours
R1337 | 30 | 48
R1430 | 360 | 346.25
R1514 | 20 | 59.5
R1517 | 120 | 143.5
R1518 | 60 | 42.75
R1527 | 60 | 30

## Dashboard
Team Resource & Planning Dashboard
Set SelectedMonth and SelectedProject in Params. Paste LP actuals into Actual_Hours. Fill planned hours + allocations to drive the resource view.
Skill Heat Map (0–5)
Engineer | FEA | CFD | Deflector development | VicFlex hose | VicFlex bracket | Vortex design | Vortex operation | Data acquisition | Fire test protocols | Failure / root cause analysis | Statistical analysis | Test fixture design | Codes and standards | Tolerance stackup
Mike | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Karl | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brian | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hannah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marcelo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Justin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aaron | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned Utilization Heat Map (Engineer x Month)
Engineer | 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10 | 2026-11 | 2026-12
Mike | 92.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Karl | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Brian | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Hannah | 85.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Marcelo | 107.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Justin | 92.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Aaron | 85.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
NPD Milestones Heat Map (Project x Milestone)
Project | DR1 | DR2 | DR3 | Launch
R1337.1 | #N/A | #N/A | #N/A | #N/A
R1337.3 | #N/A | #N/A | #N/A | #N/A
R1337.2 | #N/A | #N/A | #N/A | #N/A
R1430.1A | #N/A | #N/A | #N/A | #N/A
R1430.1B | #N/A | #N/A | #N/A | #N/A
R1430.1C | #N/A | #N/A | #N/A | #N/A
R1514.1 | #N/A | #N/A | #N/A | #N/A
R1514.2 | #N/A | #N/A | #N/A | #N/A
R1517 | #N/A | #N/A | #N/A | #N/A
R1517.1 | #N/A | #N/A | #N/A | #N/A
R1518 | 2025-02-04 | 2025-06-12 | 2026-03-13 | 2026-10-01
R1527 | #N/A | #N/A | #N/A | #N/A